## Estimation
NEW ONLINE ENGLISH TESTING SYSTEM - ESTIMATION
| Version | 0.2 | Date | 2019-12-11
| Estimated by | Lộc Dương | Approved by
The estimation for online English testing system with new test format. System contains two main sites, admin and candidate with following functions
Admin: - Manage questions - Manage tests - Manage examinations - Import questions - Assign candidates to the examination - Export user's PIN - Export test results Candidate: - Login with unit PIN - Do examination
| Task | Effort (hours)
| Requirement (Done) | 120
| Development | 684
| Test | 410.4
| Deployment | 8
| Project Management | 218.88
| Total | 1441.28

## Proposal 1 (hidden)
Proposal 1
Description: | We upgrade current system to match with new test format including Admin Site and Candidate Site and fix current issues to improve performance of this system
# | Task | Estimation (hours) | Description/Assumptions
I | Admin site | 120
1 | Question Manager | 88 | Manage all questions of tests
1.1 | Add new Section to create test with new format | 8 | Add new sections containing in new test format
1.2 | Update create question function with new section | 8
1.3 | Import questions from excel file | 40 | Current version doesn’t work
1.4 | Export questions to excel file | 32 | Current version doesn’t work
2 | Test Manager | 16 | Manage all tests
2.1 | Update "Create Test" function with new sections | 16 | Create a test by section
3 | Exam Manager | 16 | Manage exams
3.1 | Update 'Create exam' with new section | 16
II | Candidate site | 64
1 | New welcome page | 16 | Display information of exam
2 | Test page | 48
2.1 | Generate questions by new sections | 24 | From unit PIN, generate question by sections
2.3 | Control network error | 16
2.4 | Control black out | 8
III. | Current Issues | 49
1 | Sometimes, when candidates are doing the test, system stops working and candidates have to wait or press F5 to continue doing the test but Writing Section can not be saved. | 16
2 | In Listening Section, if candidates don't listen clearly and double click on play button, video will play the second time | 8
3 | Comprehension misses question. When admin create test, although create enough questions but test still missing question | 8
4 | Only system usually stops working | 8
5 | When candidates start the test, time is not enough 90 minutes, only 87 minutes or less | 9
| TOTAL | 233

## Proposal 2 (hidden)
Proposal 2
Description: | With this proposal, we upgrade Admin site from current system, only create new candidate site separately (with new APIs added)
# | Task | Estimation (hours) | Description/Assumptions
I | Admin site | 240
1 | Login API | 16 | API for user login by PIN
2 | Generate questions API | 40 | Generate questions and return API to user page
3 | Save test result API | 16
4 | Control network error, black out… | 48
5 | Question Manager | 88 | Manage all questions of tests
5.1 | Add new Section to create test with new format | 8 | Add new sections containing in new test format
5.2 | Update create question function with new section | 8
5.3 | Import questions from excel file | 40 | Current version doesn’t work
5.4 | Export questions to excel file | 32 | Current version doesn’t work
6 | Test Manager | 16 | Manage all tests
6.1 | Update "Create Test" function with new sections | 16 | Create a test by section
7 | Exam Manager | 16 | Manage exams
7.1 | Update create exam with new section | 16
II | Candidate site | 144
1 | Welcome page | 32 | Display inform about exam
2 | Start Page | 16 | Input unit PIN to enter the test
3 | Test page | 96
3.1 | Generate questions by sections | 32 | From unit PIN, generate questions by sections
3.2 | Save test result when user's doing the test | 24
3.3 | Control network error, black out… | 40
| TOTAL | 384

## Project Plan and Gantt
Project Name | New Online English Test
Project Manager
Project Deliverable
Scope Statement:
Start Date | 2018-11-23
End Date | 2019-11-23
Overall Progress | 10%
Tasks | Responsible | Start | End | Days | Status
Start to work with Dev team | Training Team | 2018-10-20 | 2018-11-14 17:09 | 20 | Complete
Set kick-off meeting | Dev Team | 2018-11-15 17:09 | 2018-11-17 | 1 | Complete
Feasible Research (give out Proposals) | Dev Team | 2018-11-18 | 2018-12-07 06:51 | 15 | Complete
Select Solution | Dev Team | 2018-12-08 06:51 | 2019-01-15 20:34 | 30 | Complete
Final Resource Plan | Dev Team | 2019-02-11 | 2019-02-17 10:17 | 5 | In progress
Implement | Dev Team | 2019-02-25 | 2019-05-03 04:48 | 43 | Not started
Testing | Dev Team | 2019-05-04 04:48 | 2019-07-08 18:31 | 51 | Not started
Pilot test the new EOST | Training Team | 2019-07-09 18:31 | 2019-08-04 11:39 | 20 | Not started
Deployment | Dev Team | 2019-08-05 11:39 | 2019-08-08 01:22 | 2 | Not started
System Testing | Dev Team | 2019-08-09 01:22 | 2019-08-10 08:14 | 1 | Not started
Officially release the new EOST | Training Team | 2019-08-11 08:14 | 2019-08-12 15:05 | 1 | Not started
Start using the new EOST | Training Team | 2019-08-13 15:05 | 2019-08-14 21:57 | 1 | Not started
Training Departement's Milestones
2018-10-01 | Start to work with Dev team
2019-11-01 | Pilot test the new EOST
2019-12-01 | Officially release the new EOST
Inform all employees of the new EOST and offer seminars of the test format
Friday, Mar 6, 2020 | Terminate the use of the current EOST and start using the new EOST
Formulas:
End = [Start]+[Days]+([Days]/7)*2
End = [Start]+[Days]+([Days]/5)*2+3+4
Start = [End, row above]+1

## Estimation of Web Front End
Details of Estimation
* This estimation is measured based on HOUR
# | Module | Section | Feature | Screen | Screen Type | Dev estimation (hours) | QA estimation (hours)
1 |  |  | Prepare Enviroment |  |  | 8 | 0
3 | Training Coordinator | Login | Login | Login email/password screen | View | 8 | 4.8
4 |  | Question Management | Create an answer | Create an answer | Add | 8 | 4.8
5 |  |  | load list answer | List answer | Search/List | 8 | 4.8
6 |  |  | Filter answer | List answer | Search/List | 8 | 4.8
7 |  |  | Create question | Create question | Add | 8 | 4.8
8 |  |  | Create a reading question section | Create question | Add | 8 | 4.8
9 |  |  | Load answers to reading question | Create question | Add | 8 | 4.8
10 |  |  | Create a listening question section | Create question | Add | 12 | 7.2
11 |  |  | Load answers to listening question | Create question |  | 8 | 4.8
12 |  |  | Create a writing question | Create question | add | 8 | 4.8
13 |  |  | View a question | View questions | View | 8 | 4.8
14 |  |  | Delete a question | Delete question |  | 8 | 4.8
15 |  |  | List of questions | Question management | Search/List | 16 | 9.6
16 |  |  | Filter questions | Question management | Search/List | 8 | 4.8
17 |  |  | Create import template excel file |  |  | 8 | 4.8
18 |  |  | Import questions | Import questions | Batch | 8 | 4.8
19 |  |  | Export questions | export questions | Batch | 8 | 4.8
20 |  | Test Management | List all tests | List all tests | Add | 8 | 4.8
21 |  |  | Create a new test | Create a test | Add | 8 | 4.8
22 |  |  | View a test | View test | View | 8 | 4.8
23 |  |  | Update a test | Update a test | Update | 6 | 3.6
24 |  |  | Delete a test | Delete a test | Delete | 4 | 2.4
25 |  | Exam Management | Create an exam | Create an exam | View | 8 | 4.8
26 |  |  | Update an exam | Update an exam | Add | 8 | 4.8
27 |  |  | Delete an exam | Delete an exam | Delete | 4 | 2.4
28 |  |  | Get list of candidates | List candidate | View | 8 | 4.8
29 |  |  | Filter candidates | List candidate | Search/List | 4 | 2.4
30 |  |  | Assign candidate to an exam | List candidate | Search/List | 8 | 4.8
31 |  |  | Exam result | Exam result | View | 8 | 4.8
32 |  |  | Edit writing result | Edit exam results | View | 8 | 4.8
33 |  |  | Send test result by email | Exam management |  | 8 | 4.8
34 |  |  | Export results to excel file | Export result | View | 8 | 4.8
35 | Candidate | Online Test | Input pin | login |  | 8 | 4.8
36 |  |  | welcome message | welcome screen | View | 8 | 4.8
37 |  |  | Exam information | Exam information | View | 8 | 4.8
38 |  |  | Writing section | Online test | View | 12 | 7.2
39 |  |  | Listening section | Online test |  | 12 | 7.2
40 |  |  | reading section | Online test |  | 12 | 7.2
Total (Hours) | [5 empty] | 314 | 188.4
DETAILS OF ESTIMATION

## Estimation of Web Back End
Details of Estimation
* This estimation is measured based on HOUR
# | Module | Section | Feature | Screen | Screen Type | Dev estimation (hours) | QA estimation (hours)
1 |  |  | Prepare Enviroment |  |  | 8
2 |  | General | Design database |  |  | 32 | 19.2
3 | Training Coordinator | Login | Login SSO with CRM | Login email/password screen | View | 16 | 9.6
4 |  | Question Management | Create an answer | Create an answer | Add | 8 | 4.8
5 |  |  | List of answers | List answer | Search/List | 8 | 4.8
6 |  |  | Filter answer | List answer | Search/List | 8 | 4.8
7 |  |  | Create question | Create question | Add | 8 | 4.8
8 |  |  | Create a reading question section | Create question | Add | 16 | 9.6
9 |  |  | Load answers to reading question | Create question | Add | 8 | 4.8
10 |  |  | Create a listening question section | Create question | Add | 10 | 6
11 |  |  | Load answers to listening question | Create question |  | 8 | 4.8
12 |  |  | Create a writing question | Create question | add | 10 | 6
13 |  |  | View a question | View questions | View | 8 | 4.8
14 |  |  | Delete a question | Delete question |  | 8 | 4.8
15 |  |  | List of questions | Question management | Search/List | 8 | 4.8
16 |  |  | Filter questions | Question management | Search/List | 8 | 4.8
17 |  |  | Import questions | Import questions | Batch | 16 | 9.6
18 |  |  | Export questions | export questions | Batch | 16 | 9.6
19 |  | Test Management | List all tests | List all tests | Add | 8 | 4.8
20 |  |  | Create a new test | Create a test | Add | 16 | 9.6
21 |  |  | View a test | View test | View | 6 | 3.6
22 |  |  | Update a test | Update a test | Update | 8 | 4.8
23 |  |  | Delete a test | Delete a test | Delete | 8 | 4.8
24 |  | Exam Management | Create an exam | Create an exam | View | 8 | 4.8
25 |  |  | Update an exam | Update an exam | Add | 8 | 4.8
26 |  |  | Delete an exam | Delete an exam | Delete | 8 | 4.8
27 |  |  | Get list of candidates | List candidate | View | 8 | 4.8
28 |  |  | Filter candidates | List candidate | Search/List | 8 | 4.8
29 |  |  | Assign candidate to an exam | List candidate | Search/List | 8 | 4.8
30 |  |  | Exam result | Exam result | View | 8 | 4.8
31 |  |  | Edit writing result | Edit exam results | View | 8 | 4.8
32 |  |  | Send test result by email | Exam management |  | 8 | 4.8
33 |  |  | Export results to excel file | Export result | View | 16 | 9.6
34 | Candidate | Online Test | Input pin | login |  | 8 | 4.8
35 |  |  | welcome message | welcome screen | View | 8 | 4.8
36 |  |  | Exam information | Exam information | View | 8 | 4.8
37 |  |  | Writing section | Online test | View | 16 | 9.6
38 |  |  | Listening section | Online test |  | 16 | 9.6
39 |  |  | reading section | Online test |  | 16 | 9.6
Total (Hours) | [5 empty] | 370 | 222
DETAILS OF ESTIMATION

## Detailed Estimation (hidden)
Detailed Estimation
Description: | With this proposal, we create a new system, only using login and save candidate's test result API from current system
# | Task | Estimation (hours) | Description/Assumptions
I | General | 138
1 | Login | 24 | Login function of this site uses API from CRM system
1.1 | Login user interface | 8 | Create user login interface
1.2 | Login API | 18 | Implement login Api from CRM system
2 | Save user's test result API | 48 | Design database
3 | Database Design | 40 | When user finish the test, save user's test result to CRM system
II | Admin site | 576
1 | Questions Manager | 200 | Manage all questions of tests
1.1 | List of questions | 32
1.1.1 | Display contents of quentions on the list | 8 | Create a list of questions, 20 questions per page
1.1.2 | Filter questions | 16 | Filter question by content or id
1.1.3 | Pagination | 8
1.2 | CRUD questions | 110 | Create, read, update, delete questions. Questions are create differently by sections.
1.2.1 | Create question | 30
1.2.1.1 | Create reading question | 16
1.2.1.2 | Create listening question | 16
1.2.1.3 | Create writing question | 16
1.2.2 | Read question | 8
1.2.3 | Update question | 16
1.2.4 | Delete question | 8
1.3 | Filter questions by content | 8 | Filter questions by content, id, section. Display filter result
1.4 | Import questions from excel file | 34
1.4.1 | Create import format excel file | 2
1.4.2 | Implement import service to import question | 32
1.5 | Export questions to excel file | 16
3 | Test Manager | 64 | Manage all tests
3.1 | Test List | 24
3.1.1 | Display contents of tests on the list | 16 | Create a list of tests 20 tests per page
3.1.2 | Filter tests | 8 | Filter test by Id or title
3.1.3 | Pagination | 6
3.2 | CRUD Tests | 40 | Create test by section
3.2.1 | Create Test | 32 | Questions of test are generated randomly or not
3.2.2 | Read Test | 8
3.2.3 | Update Test | 16
3.2.4 | Delete Test | 8
4 | Exam Manager | 312 | Manage exams
4.1 | Exam List | 48
4.1.1 | Display contents of exam on the list | 32 | Create a list of exams 20 exams per page
4.1.2 | Filter exams | 16 | Filter exam by exam title or candidate name, test, date from to.
4.2 | CRUD exam | 68
4.2.1 | Create Exam | 32
4.2.2 | Read Exam | 10
4.2.3 | Update Exam | 16
4.2.4 | Delete Exam | 10
4.3 | Filter exam | 16 | Filter by user, date, section
4.4 | Assign user to the exam | 48 | Filter user to select from, Each user has only unit PIN
4.4.1 | Get List User | 32
4.4.2 | Filter user | 8
4.4.3 | Assign user | 8
4.5 | Export Assigned users to excel file | 16 | After assigned users to exam, can export user with their PIN to excel file
4.6 | View Exam result | 32 | View result of each user
4.7 | Give mark to writing section | 50 | User can give comment, give mark to writing section
4.8 | Export Exam result | 32
4.9 | Send exam result to user by email | 18
4.1 | Convert exam result to company level | 32
III | Candidate site | 172
1 | Welcome page | 32 | Display inform about exam
2 | Start Page | 8 | Input unit PIN to enter the test
3 | Test page | 132
3.1 | Generate questions by sections | 40 | From unit PIN, generate question by sections
3.2 | Save result when user's doing the test | 32
3.3 | Control network error, black out… | 60
| TOTAL | 886

## Technical Requirements
Technical Requirements
Develop Area | Item | Description
Deployment Environment | Backend OS type | Window server 2008 64bit
| Web server | Wampserver 2.4
| PHP version | >=5.6
| MySQL version | >=5.5
| Apache version | >=2.4
Testing Environment | Web browser | OS: Windows 7 64bit: - Firefox version 48.0.2 (latest version) - Chrome version 55.0 (latest version) OS: Windows 10: - Edge version 38.14393 (latest version)
Development technology | Backend technology | Zend expressive
| Web single page | Reactjs
| Offline synchronization | Not support

## Master Schedule
I. Schedule
# | Team | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28
A | Front End
D | Back End
SPRINT #2
- Section Manage Page
- Test Manage Page
SPRINT #5
_ List Test
_ Create test
_View a test
_ Update Test
_ Delete Test
SPRINT #1
_Prepare Enviroment
_Design Database
_ Login
Lễ Chiến thắng và quốc tế lao động
Lễ Quốc Khánh
Giáng Sinh
Giỗ Tổ
SPRINT #3
- Exam Manage Page
SPRINT #6
_ Create Exam
_ Update Exam
_ Delete an exam
_ Get list of candidates
_Filter candidates
SPRINT #7
_ Assign candidate to an exam
_ Input pin
_welcome message
_ Exam information
SPRINT #8
Online Test
_ Reading section
_ Reading section
_ Listening Section
SPRINT #4
_ Candidate Online Test Page
SPRINT #9
Online Test
_ Exam result
_Edit writing result
_Send test result by email
_Export results to excel file